## SOW.BOQ
SOW YI023 Falalop Multipurpose Community Center
S/No | Activities | Code | No | L (ft.) | W (ft.) | H/D (ft.) | Quantity | Unit | Cost
1 | General Requirements
1.1 | Mobilization/Demobilization and Transport Cost |  | 1 |  |  |  | 1 | lot
2 | Layout and Excavation
2.1 | Clearing/ Disposal/Layout |  | 1 | 150 | 64 |  | 9600 | sq.ft
2.2 | Excavation/Backfilling/Disposal of excess excavated materials | [5 empty] | 13484.8 | cu.ft
| total | [7 empty] | 0
3 | Concrete Works
3.1 | Footing (2,093.24 ft.3), Footing Tie Beam (925.35 ft.3), Pedestal (299.35 ft.3) and Slab on Grade Extension (1,384.34 ft.3) including formworks and other work items necessary in the completion of work, including setting of Anchor bolts and setting templates |  | 1 |  |  |  | 4702.28 | cu.ft
4 | Construction/Erection of Steel Columns, Beams, Rafters, Roof Framing and etc.
4.1 | Installation of Building Frame and all its accessories in accordance with erection plans, including the necessary tools and equipment to complete the work items. |  | 1 |  |  |  | 1 | lot
5 | Installation of Roofing Materials
5.1 | Installation. Ga 24 bended corrugated sheets/gutters/downspout including its fasteners and accessories, as shown on plans |  | 1 |  |  |  | 1 | lot
6 | Water Tanks and piping
6.1 | Installation of PVC tanks, piped in series with faucets, strainer and valves |  | 4 |  |  |  | 4000 | gals
7 | Installation of Electrical/ Fixtures
7.1 | Installation of Lighting and Power lines |  | 1 |  |  |  | 1 | lot
8 | Painting Works
8.1 | Painting Works |  | 1 |  |  |  | 1 | lot
9 | Installation/construction of Basketball board/ring/ball-complete full court including painting |  | 1 |  |  |  | 1 | lot
[7 empty] | TOTAL LABOR COST |  | 0

## SCHED
Project Title: |  | YI023 Falalop Multipurpose Community Center
Location: |  | Falalop
PRN No.: |  | YI023
Subject: |  | Construction Schedule
Duration (WEEK) |  | 10 WEEKS
NO | ACTIVITIES | Total Amount | MC | MC + ST | LC | TDC | others MU | service tax | Rel.Weight (%) | No. | DURATION (WEEKS)
|  |  |  | 106% | 40% |  | 125% | 105% |  | weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
1 | Mobilization/Demobilization and Transport Cost | 2625 |  |  |  | 2000 | 2500 | 2625 | #REF! | 1
2 | Layout and Excavation | 26623.8 |  |  |  | 20284.8 | 25356 | 26623.8 | #REF! | 2
3 | Concrete Works | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4
4 | Construction/Erection of Steel Columns, Beams, Rafters, Roof Framing and etc. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4
5 | Installation of Roofing Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 3
6 | Water Tanks and piping | 38870.748 | 20284.8 | 21501.888 | 8113.92 | 29615.808 | 37019.76 | 38870.748 | #REF! | 2
7 | Installation of Electrical/ Fixtures | 36592.71 | 19096 | 20241.76 | 7638.4 | 27880.16 | 34850.2 | 36592.71 | #REF! | 3
8 | Painting Works | 74584.2825 | 38922 | 41257.32 | 15568.8 | 56826.12 | 71032.65 | 74584.2825 | #REF! | 2
9 | Installation/construction of Basketball board/ring/ball-complete full court including painting | 2924.964 | 1526.4 | 1617.984 | 610.56 | 2228.544 | 2785.68 | 2924.964 | #REF! | 2
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Relative % of Accomplishment | [10 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cumulative % of Accomplishment | [10 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
MANPOWER SCHEDULE
1 | Engineer | [9 empty] | 2
2 | Foreman | [9 empty] | 2
3 | Skilled Workers | [9 empty] | 12
4 | Helpers | [9 empty] | 25
EQUIPMENT SCHEDULE
1 | Service Vehicle (Land) | [9 empty] | 1
2 | Service Vehicle (Sea) | [9 empty] | 1
3 | Heavy Equipment | [9 empty] | lot
4 | Power Generator | [9 empty] | 2
5 | Power Tools | [9 empty] | lot
6 | Misc. Hand Tools | [9 empty] | lot