## BOQ without Cost
IOM SHELTER AND SETTLEMENT PROJECT
Bill Of Quantity ( Engineer's Estimate)
Project/Job Title: Upgrade Storm Drainage and Internal Road - Gayarah Emergency Airstrip Camp
Location: Qayarah district
| Estimated Project Duration: 30 days from the date of signed the contract |  | Date: 06 June 2018
General Guidelines 1-Design plans and BoQ are complementary to each other, hence the contractor has the obligation to execute the tasks mentioned in either one of them. Incase BOQ and technical drawings have descrepencies. BOQ supercedes technical drawings. Follow IOM site engineers site instruction at all times. 2- All the BoQ articles comprise supplying manpower, machinery, equipment, trnsportation all necessary requirements to get the work done properly regardless of it's mentioned in the BoQ articles or not. 3- All the BoQ articles must be carried out according to guidelines of Iraqi Technical Specifications with updates and instructions of IOM site engineers 4- All the BoQ articles comprise removing and transporting any debris or rubble to allocated disposal areas by municipality or local authority 5.Any damages to other structure or tents in the camp will be a responsibility of the contractor to redo and fix it Without claiming any compensation from IOM 6. subbmit workplan schudule for project activities 7.Site visit is reqiured for contractors to see camp site.
Technical Specifications 1. Contractor required to undertake site topography survey mark total station reading areas with high rain fall and storm water runoffs, 2. Contractor will submit AS build drawings for upgrading storm water drainage system ( open channel, culverts, berms, roads, secondary draianges etc ) 3. conctractor will submit letter undertaking site assessment was undertaken understand site condition, willing to perform construction at own risk, without requesting additional variation cost in the project 4) Contractor will restudy IOM storm drainage design for long term susutaianblity of the camp from flooding. Contractor will provide 12 months warranty in remedial measures if any unwarenty flooding happens due to inadequate work in place 5. Open channel draiange will be trapezoidal, weak sidewall compacted and stablized from collapse. provide side wall protection if necessary 6) Machinery for earth dam ( Berm) should be sheep type roller, 17-20 ton , suitable type B grade earth materials, compacted each layer 25cm to 95% compaction 7) placement shotcrete concrete C20 grade, WC ratio 100mm slump, 8. pedestrian bride constructed by steel plate ( HSS 10cm x 10cm x 4mm) frame, with cross bracing support 9. Internal road will be resurfaced , secondary drain cleaned off debris, new subgrades layer. resurfaced road will act as internal drainage and secondary drain leadind to main storm drain .
| CIVIL INFRASTRUCTURE - Open Channel Storm Drainage Upgrading | Unit | Quantity | Unit Price | Total Price | Technical Specifications / Remarks
1 | Trapezoidal open drainage channel (outside Airstrip camp in front of sector H" till sector N)
1.a | Supply all required Machinery, equipment’s, tools and resources (manpower), excavation in all types of ground (even rock layers or existing foundation concrete & Asphalt layer, if any) including compaction for the base of excavation, to make a trapezoidal open drain channel with dimension of Bottom width (base) 4.5m, Top width 7m and Depth 2m (Variable depending on surveyor leveling to discharge the stormwater) with sloping min. 2 %, in front of the earthen dam (2m away earth dam) between Airstrip and Jadah(4,5 & 6), the subcontractor should use the soil that gets it from the excavation to backfill the existing drainage with compaction by sheepsfoot compactor, contractor shall reuse the extra soil resulting from the excavation according to the determination of the supervising IOM engineer | M.L | 2400 |  |  | As attached design As shown in the site plan, marked it as 1.a
2 | Earthen Beam (Dam) / outside Airstrip camp in front of sector H" - sector N
2.a | prepare and level the ground with grader, cleaning debris, construct earth dam with suitable sub-base type B layer by layer (25 cm maximum), compaction by using the sheep roller compactor 95% every layer, earthen Beam with dimension Bottom width (base) 5m, Top width 1.5m and 2.5m Height, the location is between Airstrip and Jadah(4,5 & 6), Parallel and 2m away with the previous item (Trapezoidal drainage), | M.L | 2400 |  |  | As attached design As shown in the site plan, marked it as 2.a
3 | Trapezoidal open drainage channel (outside Airstrip camp in front of sector D till sector G)
3.a | Supply all required Machinery, equipment’s, tools and resources (manpower), to widening and deepening existing drainage between Airstrip and Jadah 3, the excavation will be in all types of soils(even rock layers or existing foundation concrete & Asphalt layer, if any) including compaction for the base of excavation, to make a trapezoidal open drain channel, with dimension of Bottom width (base) 6m, Top width 8m and Depth about 2m (Variable depend on surveyor leveling to discharge the water) with sloping min. 2%, contractor shall reuse the soil resulting from the excavation according to the determination of the supervising IOM engineer | M.L | 1000 |  |  | As attached design As shown in the site plan, marked it as 3.a
4 | Trapezoidal open drainage channel (inside Airstrip camp between sector K&L continues between sector D&E)
4.a | Supply all required Machinery, equipment’s, tools and resources (manpower), perform widening and deepening existing main drainage inside Airstrip between sector K&L continues to sector D&E to receive water from the drainage from Jadah (4,5 & 6 ), discharch the storm water into drainage in front of Jadah 3, excavation will be in all types of soils(even rock layers or existing foundation concrete & Asphalt layer, if any) including compaction for the base of excavation, to make a trapezoidal open drain channel, with dimension of Bottom width (base) 5m, Top width 7m and Depth 1.5 to 2m (Variable on surveyor leveling to discharge the water) with sloping min. 2 %, The contractor shall reuse the soil from the excavation according to the determination of the supervising IOM engineer | M.L | 600 |  |  | As attached design As shown in the site plan, marked it as 4.a
5 | Concrete work
5.a | Prepare site, Supply required equipment, tools and resources (manpower), provide shot crete concrete 1:2:4 (C20), 10 cm thickness for both faces with the base of inside the trapezoidal open drainage using BRC 10*10 thickness 4 mm,Price Includes Laying One Layer 6mm vapor barrier ( Nylon ) and curing for concrete by water three times per day for 7 days from casting date, the work will be for the Trapezoidal open drainage channel (inside Airstrip camp between sector K&L continues between sector D&E) | M2 | 10000 |  |  | As shown in the site plan, marked it as 5.a
6 | CMU wall
6.a | Supply Materials (Solid Block 15*20*40cm, cement, sand and water) with all required equipment’s, tools and resources (manpower), to build a wall (40cm width and about 2m high, Variable depend on surveyor leveling ) by using cement mortar(1:3), the work will be inside the intersection of open drainage, and then do the cement plastering for both face inside and outside of the wall, with painting by waterproof material, the price include curing the wall building and cement plastering by water three times per day for 7 days from implementation date, according to the specifications, details and instructions of IOM site engineer. | M2 | 100 |  |  | As shown in the site plan, marked it as 6.a
7 | Road Crossing (90 cm inside diameter concrete reinforcement pipe)
7.a | Supply all required equipment’s, tools and resources (manpower) and doing excavation according to the profile or surveyor leveling in all types of soils(even old concrete pipe, rock layers or existing foundation concrete & Asphalt layer, if any) including compaction for the base of excavation, then casting concrete 1:2:4 (C20) thickness 10 cm for the base of excavation and install a concrete reinforcement pipes (90 cm inside diameter), and casting concrete for around the pipe not less than 15cm and using Reinforced concrete @12mm 15*15cm for the above of pipe and then back fill with suba-base and compaction ( see drawing), according to the specifications, details and instructions of IOM site engineer. | M.L | 100 |  |  | As attached design As shown in the site plan, marked it as 7.a
8 | Pedestrian Crossing
8.a | made in steel 1.5m width , 8m lenght (Variable) Pedestrian Crossing, using hollow steel pipe (HSS) with dimensions 100*100*3 mm, with cross brange support at 1m c/c, install 10mm plywood top and steel checker plate 3 mm thickness with steel bolts each 20cm c/c, install handrail 1.5m high using (HSS) 50*50*2 mm, handrail must be welded with a steel vertical column each 1 m, and a 3 line horizontal member using the same section, use (HSS) 100*100*3 mm to support the pedestrain bridge every 2m c/c installed on concerete base, all steel parts painted with layer of anti-rust paint and two layer oil paint grey color, all the work to be done according to the instructions of the supervisor engineer, see attached drawing. | Pec | 20 |  |  | As attached design As shown in the site plan, identify by IOM site engineer
9 | Internal Roads Upgrade in sector ( A, H", H, I, J, K, L, M and N)
9.a | Supply all required Machinery, equipment’s, tools and resources (manpower) to Clean, widening and deepening existing secondary drains on both side of road in sectors (A, H", H, I, J, K, L, M and N), to discharge storm water from the blocks into the nearest open trench storm drain collection point,The Secondary drainage should be 45degree, 30cm Top width and 60cm deep in trapezoidal sectional shape (see drawing) | M.L | 65000 |  |  | As attached design As shown in the site plan, marked it as 9.a
9.b | Cut the damage layer of existing sub-base in the internal roads in sectors (A, H", H, I, J, K, L, M and N) which identify by IOM engineer, supply a new sub-base (type B) to place in layer 15-20 cm thickness with compaction 95% , and should keep the road section design (3% slope Camber on transverse section) see the road transverse section in attach,follow IOM site engineer,The contractor shall reuse the old sub-base inside the camp according to the determination of the supervising IOM engineer | M2 | 20000 |  |  | As attached design As shown in the site plan, marked it as 9.a
9.c | Supply and Install (Spiral pipe (French drain) with 20cm inside diameter) with all required Machinery, equipment’s, tools and resources (manpower) in sectors (A, H", H, I, J, K, L, M and N) which identify by IOM engineer and install the pipe according to the profile or surveyor leveling to make a crossing for internal roads, minimum 2% sloping, to discharge water from block to block to gravity flow to main storm drain, casting concrete around the pipe not less than 10cm using BRC 10*10 thickness 4mm for the Top concrete cover of pipe,according to the specifications, details and instructions of IOM site engineer. | M.L | 1000 |  |  | As attached design As shown in the site plan, marked it as 9.a
Overall Total Estimated Cost
IOM International Organization for Migration

## Work Schedule
Work Schedule
Storm Drainage and Internal Road Upgrade - Gayarah Emergency Airstrip camp
Implementation Work Schedule :
| No | Activity Description ( Refer BOQ) | Planned Start | Planned Finish | % Completion | 2018-06-01 | 2018-07-01 | 2018-08-01 | Comments
| 1 | Activity - A | [6 empty] | Constractor responsibility to conduct site inspection prior to submitting bid price. Refer BOQ general instruction for no cost time extension .
| 2 | Activity -B
| 3 | Activity C
| 4 | Activity D
| 5 | Activity E

## Site Photos
EXISITING OPEN CHANNEL STORM DRAINAGE IN GAYARAH AIR STRIP